## Sheet1
Monique Reserve Offset Worksplan 2014-15 SEEDS
Activity ID | Location | Team Leader | Methodologies | Descriptions | Quantifiable Outcome | Timing | Budget
Monique1 | Offset site 1 |  | Map Site Boundaries & Establish Photo Points - Prior to commencement of works provide GPS coordinates for site perimeters and establish photo points (minimum of two points, dependant on the site). |  | Production of map showing boundaries, work zones and photo points. Establishment of permanaent photo point in form of a star picket | Prior to Commencing Works | 226
Monique 2 | Offset site 1 |  | Woody Weeds and Blackberry - Cut/paint and hand pull throughout entire site on 2 occasions. Small Sallow wattle and scattered Blackberry |  | Treatment of all Woody Weeds and Blackberry | July and February | 1356
Monique 3 | Offset site 1 |  | Ground Flora Weed Control - Handweed and knapsack all ground flora weeds within the site and selected track edges on 6 occasions as per map. Orchid colonies will be handweeded and no herbicide application in this zone. Both Glyphosate and Fusilade will be used |  | Treatment of all ground flora weeds on 6 occasions | July, September, October, November, January and May | 5424
Monique 4 | Offset site 2 |  | Woody Weeds and Blackberry - Cut/paint and hand pull Woody Weeds and Blackberry throughout entire site on 2 occasions. Small Sallow wattle and scattered Blackberry |  | Treatment of all Woody Weeds and Blackberry | July and February | 226
Monique 5 | Offset site 2 |  | Ground Flora Weed Control - Handweed and knapsack all ground flora weeds within the site and track edge on 6 occasions as per map. Orchid colonies will be handweeded and no herbicide application in this zone. Both Glyphosate and Fusilade will be used |  | Treatment of all ground flora weeds on 6 occasions | July, September, October, November, January and May | 1695
Monique 6 | Whole Site |  | Annual Report - Submission of Annual Reports detailing works completed, including annual photo reports |  | Production of an Annual Report | By June 30 each financial year | 226
[6 empty] | TOTAL (Excl GST) | 9153